## Sheet1
|  |  | April |  |  |  | May |  |  |  | June
Team | Status | Release | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Mobile / Frontend | Not Started | 2nd Apr | April Week 1: Sign Up and Login
| Not Started | 6th Apr | April Week 1: Homepage
| Not Started | 12th Apr | April Week 2: Profile Page
| Not Started | 25th Apr | April Week 2: Booking System
| Not Started | 28th Apr | April Week 4: Payment
| Not Started | 1st May | May Week 1: Arena Details Page
| Not Started | 5th May | May Week 1: Dashboard
| Not Started | 6th May | May Week 1: Feedback and Rating
| Not Started | 9th May | May Week 1: Location
| Not Started | 18th May | May Week 2: Payment new phase
| Not Started | 19th May | May Week 2: Supprt/Helpline
| Not Started | 28th May | May Week 2: Player Selection
| Not Started | 30th May | May Week 4: Team Registration
| Not Started | 2nd Apr | April Week 1: SignUp/login
Backend | Not Started | 4th Apr | April Week 1: Search Filter
| Not Started | 10th Apr | April Week 1: Booking System
| Not Started | 6th April | April Week 1: Payment
| Not Started | 10th Apr | April Week 1: Profile Page
| Not Started | 12th Apr | April Week 2: Arena Details Page
| Not Started | 12th Apr | April Week 2: Dashboard
| Not Started | 13th Apr | April Week 2: Feedback and Rating
| Not Started | 14th Apr | April Week 2: Location
| Not Started | 16th Apr | April Week 3: Payment new phase
| Not Started | 2nd May | April Week 3: Palyer Selection
| Not Started | 17th Apr | April Week 3: Team Registration
Design | Not Started | 1st Apr | April Week 1: Sign Up and Login
| Not Started | 2nd Apr | April Week 1: Homepage
| Not Started | 4th Apr | April Week 1: Profile Page
| Not Started | 15th Apr | April Week 1: Booking System
| Not Started | 17th Apr | April Week 3: Payment
| Not Started | 18th Apr | April Week 3: Arena Details Page
| Not Started | 25th Apr | April Week 3: Dashboard
| Not Started | 26th Apr | April Week 4: Feedback and Rating
| Not Started | 27th Apr | April Week 4: Location
| Not Started | 3rd May | May Week 1: Payment new phase
| Not Started | 4th May | May Week 1: Support/ Helpline
| Not Started | 11th May | May Week 1: Player Selection
| Not Started | 12th May | May Week 2: Team Registration